## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 2 | US001 | As a System Architect, I want to analyze the existing IVR architecture and define integration requirements with ACS so that the legacy system can be modernized with cloud communication capabilities. | MUST HAVE | Architecture analysis | System Architect | 3- Completed
Sprint 2 | Sprint 2 | US002 | As a Cloud Engineer, I want to configure Azure Communication Services call automation APIs so that incoming customer calls can be handled by the IVR application. | MUST HAVE | IVR architecture design | Cloud Engineer | 3- Completed
Sprint 2 | Sprint 2 | US003 | As a Backend Developer, I want to implement IVR menu logic and service APIs so that customer requests such as PNR enquiry or train information can be processed. | MUST HAVE | ACS communication APIs ready | Backend Developer | 3- Completed
Sprint 3 | Sprint 3 | US004 | As an AI Engineer, I want to integrate speech-to-text, text-to-speech and intent recognition modules so that the IVR system can understand natural language requests. | MUST HAVE | IVR backend APIs ready | AI Engineer | 3- Completed
Sprint 4 | Sprint 4 | US005 | As a DevOps Engineer, I want to deploy and monitor the conversational IVR system on cloud infrastructure so that the service remains scalable and reliable. | COULD HAVE | Conversational AI integration | DevOps Engineer | 3- Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US001 | T1 | Study traditional IVR architecture and define integration points for ACS | 2026-02-09 | 2026-02-10 | System Architect | Design | 3- Completed | 6 | bar: Day 1 to Day 2
US001 | T2 | Design IVR system architecture aligned with ACS communication services | 2026-02-18 | 2026-02-19 | System Architect | Design | 3- Completed | 8 | bar: Day 2 to Day 3
US002 | T3 | Configure communication APIs and call handling workflow using Azure Communication Services | 2026-02-22 | 2026-02-24 | Cloud Engineer | Build | 3- Completed | 8 | bar: Day 3
US003 | T4 | Develop backend IVR APIs and menu routing logic | 2026-02-25 | 2026-02-26 | Backend Developer | Coding | 3- Completed | 10 | bar: Day 3 to Day 5
US004 | T5 | Implement speech-to-text, text-to-speech, and intent recognition modules | 2026-03-07 | 2026-03-08 | AI Engineer | Coding | 3- Completed | 8 | bar: Day 6 to Day 7
US005 | T6 | Integrate all modules and deploy conversational IVR prototype | 2026-03-13 | 2026-03-14 | DevOps Engineer | Coding | 3- Completed | 6 | bar: Day 8 to Day 9
US005 | T7 | Perform end-to-end testing of the conversational IVR system | 2026-03-22 | 2026-03-22 | DevOps Engineer | System Test | 3- Completed | 4 | bar: Day 12
US005 | T8 | Validate system performance after integration and deployment | 2026-03-25 | 2026-03-25 | DevOps Engineer | Regression Test | 3- Completed | 4 | bar: Day 13
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 3 | Difficulty understanding legacy IVR workflow and system requirements | Reviewed documentation and clarified system architecture before proceeding
Sprint 2 | Day 6 | Issues configuring communication APIs for IVR simulation | Tested API endpoints locally and validated request-response workflow
Sprint 2 | Day 10 | Errors while implementing IVR menu routing logic | Debugged backend code and corrected menu handling logic
Sprint 3 | Day 9 | Problems integrating speech-to-text and intent recognition modules | Adjusted speech processing functions and tested conversational flow
Sprint 4 | Day 12 | Minor bugs identified during system testing and integration | Performed debugging and updated backend logic before final testing

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2026-02-02 | 2026-02-16 | System Architecture Team | Document IVR architecture and system workflow clearly | Starting development without analyzing legacy IVR | Collaborating during system design discussions | Created architecture diagram and requirement document
2 | 2 | 2026-02-16 | 2026-03-02 | Backend Team | Use proper API structure for IVR services | Writing unstructured backend logic | Testing API responses during development | Implemented structured FastAPI endpoints for IVR menus
3 | 3 | 2026-03-02 | 2026-03-16 | AI Development Team | Implement speech processing modules step-by-step | Integrating AI modules without testing individually | Evaluating speech-to-text and intent recognition accuracy | Completed conversational AI integration testing
4 | 4 | 2026-03-16 | 2026-03-28 | DevOps + Backend Team | Perform system testing before final deployment | Waiting until the end to test system integration | Regular debugging and module validation | Completed end-to-end testing and finalized IVR prototype